## Cover Page
VENUE BOOKING SYSTEM
Product Backlog
|  | Prepared By / Last Updated By | Reviewed By | Approved By
| Name | Shamini S, Ravi Teja Domakonda​ Bhamini Poorna Gurram,Bartick Chatterjee​,Dhanashree Patil​
| Role | POD Members
Signature
Date
Release ID: QTAD-PBL / 2.0.0 / 30-Mar-2015 |  |  |  | C3: Protected
Controlled copy
Controlled copy
Controlled copy
Controlled Copy

## Instructions
Product Backlog Instructions C3: Protected Controlled Copy
Backlog Worksheet
This sheet has to be filled while doing "Create Product Backlog" task in the Initial Envisioning Phase.
The Product backlog worksheet contains a list of features/requirements that the business would want to implement in an application. This worksheet would continue to exist from the beginning to the end of the project. The Product Owner maintains it by adding, modifying, removing any of the items listed there. They can also change the priority of the items so long as they are not being worked by the team in the ongoing Sprint. Most of the re-ordering would happen just before the Sprint Planning meeting. To ensure this kind of continuous update, this worksheet could be re-visited during periodic intervals once during the release elaboration Phase and thereafter during the project execution. The changes to the Product backlog could be triggered from several sources in terms of inclusion of new features / bugs/ known issues based on the stakeholder requests and the effort, schedule for the same would also be re-visited in the product backlog worksheet. Fill the following fields in the product backlog worksheet for each feature.
| User Story ID | <Provide unique ID for each User story>
| User Story Name | <Provide the theme/name of the User story or a high level requirement> Eg: User login Registration Mail notification
| User Story Role | < Provide who would be end User of the User story>. Details of who would use that functionality Eg:End User Admin Teacher Conference attendee
| User Story Details | <Provide description of what the User want> Provide details on "As a/an" particular user what the user wants. Eg: As a conference attendee, I want to be able to register online
| Acceptance criteria | <Specify the Acceptance criteria> Acceptance criteria define the boundaries of a user story, and are used to confirm when a story is completed and working as intended. So for the above example, the acceptance criteria could include: A user cannot submit a form without completing all the mandatory fields Information from the form is stored in the registrations database.
| Sprint | Sprint in which the user story is planned to completed. Select it from the drop down. Story Point is given in Fibonacci series of upto 21. For any User story if the estimation goes beyond 21, then the user story has to be broken down.
| Story point | A story point is a metric used in agile project management and development to determine (or estimate) the difficulty of implementing a given story. Select the story point that will be assigned to the user story from the drop down (in Fibonacci series) during the sprint planning meeting while estimating an user story.
| Done | Yes/No field, that can be selected from drop down based on an user is completed or not
| Added in Sprint | Provide sprint number when the particular User Story was handled
| Closed in sprint | Provide sprint number when the particular User Story was completed
| Actual Story Points | Actual story point burned for an user story while developing. Select from the drop down (in Fibonacci series)
Charts
| Sprint | This value is non-editable. Represents the Sprint numbers
| Story Points remaining | Enter the total story points calculated for the Sprint.
| Done | Enter the total story points that was "Done" in the sprint
| Variation | This value is non-editable. Variation is calculated as [(Current sprint's story point remaining + done) - (Previous sprint's story point remaining + done) + Previous sprint's variation]
| Percent Complete | Percentage completed is calculated as [(Done story point of the sprint/(Done story point + story point remaining)) *100]
| Release Burn Down Chart | 1. A typical release Burn Down chart would enable the Product Owner to assess as to how each iteration is progressing towards realizing the release goal. They would be able to assess the number of features that are going to make it (or) not make it to the release based on the number of features delivered by the team in each iteration. 2. Based on the progress being made by the team, the Product Owner may decide to add more Sprints within a release (if it is a feature driven release) or cut down some of the features from the Release backlog (if it is a Date driven release). The release burn down chart would be automatically plotted based on the data given on the Release burn down table with story points remaining and the done.

## Backlog
Product Backlog VENUE BOOKING SYSTEM Project ID: POD2 C3: Protected Controlled Copy
Done
User Story Id | User Story Name | User Story Role | User Story Details | Acceptance criteria | Sprint | Story Point | Done | Added in Sprint | Closed in sprint | Actual Story Points
US_01 | Dealer Login | Dealer | Dealer should be able to login with valid credentials | Step 1: Application opens with a login option. | 1 | 3 | Yes | 1 | 1 | 3
Step 2: Dealer can login with valid Credentials
US_02 | Dealer Registration | Dealer | Dealer needs to be registered in the application before getting logged in. | Step1:Applications gives a registration form to be filled by new dealers | 1 | 2 | yes | 1 | 1 | 2
Step2:The registration form should contain inputs such as
Username,firstname,lastname, DOB, email,
Password,Type of user.
Step 3: After Validation it will be aded in the dealer list.
US_03 | Customer Registeration | Customer | Customer needs to be registered in the application before getting logged in. | Step 1: Appication gives a registeration form to be filled by new customers | 1 | 2 | yes | 1 | 1 | 2
Step 2:The registration form should contain inputs such as
Username,firstname,lastname, DOB, email,
Password,Type of user.
US_04 | Customer login | Customer | Customer should be able to login with valid credentials | Step 1: Application opens with a login option. | 1 | 3 | yes | 1 | 1 | 3
Step 2: Customer can login with valid Credentials
US_05 | Venue Registration | Dealer | As a dealer, He should be able to register with atleast one venue | Step 1: Application gives a venue registration form. | 1 | 2 | yes | 1 | 1 | 2
Step 2: The registration form should contain inputs such as type of venue (Halls, Auditoriums, Restaruants, Hotels), location, Venue Name
Step 3: After completing the registration form the venue will be added to the venue list.
US_06 | View venue status | Dealer | The dealer can view the customer requests and accepts. | Step 1: After login the dealer can view the list of venues he has registered. | 2 | 3 | yes | 2 | 2 | 3
Step 2: From the list the dealer can view the number of booking requests for a particular venue.
Step 3: Dealer can accept or reject the customer requests.
US_07 | Request Payment | Dealer | The dealer requests the customer for the payment confirmation. | After the dealer accepts the customers request, the dealer sends a reminder for payment confirmation along with payment details. | 2 | 5 | yes | 2 | 2 | 5
US_08 | Search venue | Customer | The customer can search for the required venue | Step 1:Customer will search for the venues based on the location. | 2 | 3 | yes | 2 | 2 | 3
Step 2: Then Customer will see the list of venues available in that location
US_09 | Book Venue | Customer | The customer will book the venue according to his requirement. | The customer can book any one of the available venues and the request will be forwarded to the Dealer | 1 | 5 | yes | 2 | 2 | 5
US_10 | Manage Venue Requests | Dealer | The dealer can edit the venue details | Step1 : The dealer accepts the customer requests and sends a reminder. | 2 | 3 | yes | 2 | 2 | 3
Step 2: The customer makes the payment if the venue is confirmed.
US_11 | Admin Login | Admin | As an admin , I should be able to log in using credentials. | Step1:Application opens with a toggle option for Admin, dealer and customer login. | 1 | 3 | yes | 1 | 1 | 3
Step2:Admin can login using his credentials
US_12 | View users | Admin | Admin will be able to view the list of registered customers , dealers | Admin will have access to the customer information and also the venues registered by the dealers. | 1 | 3 | yes | 1 | 1 | 3
US_13 | Customer Payment | Payment | Customers can select anyone of the payment options | Step 1: Appication gives a payment form to be filled by customers | 2 | 5 | yes | 2 | 2 | 5
Step 2:The registration form should contain inputs such as
Dealer Username, Amount, Payment options, Customer Username.
Step 3: After the payment is successful , the customer and dealer will be provided with the transaction id.
US_14 | Manage MY Profile | Dealer/Customer | The users can view or update their details | The users will be able to view their details. If they need to change anything they can update their information and save it. | 1 | 2 | yes | 2 | 2 | 2
US_15 | Manage Venue | Dealer | The dealer can update or delete the details of the venue | After the dealer is logged in with valid credentials he has access to modify the details of the venues registered by him. He can Add , Update and Delete Venue details. | 2 | 3 | yes | 2 | 2 | 3
US_16 | Logout | Dealer/Customer/Admin | The user should be able to logout from the website | Admin/User can click on the logout button when he wants to logout. | 1 | 2 | yes | 1 | 1 | 2

## Charts
Release Burndown
Only edit shaded columns, others are calculated
Sprint | Story points |  |  | Percent Complete | Min | Max
| Remaining | Done | Variation
1 | 100 | 75 | 0 | 43% | 0 | 100
2 | 170 | 150 | 145 | 47% | -145 | 25
3 | 190 | 120 | 135 | 39% | -135 | 55
Yes
No

## Sheet1 (hidden)
0
5
10
20
30
50
80
130
200
400
1000